## Summary
GW Ranch / Pacifico / Amazon — Latest Filings Review
Pecos County, TX · public filings through 2026-08-18 · Land Resource Partners · not investment advice
Headline | Amazon confirmed (Aug 7, 2026) it acquired the 8,000-ac GW Ranch site; Pacifico Energy remains power developer and will sell Amazon power.
Trigger | Three Amazon TDLR construction registrations (TABS2026026954/-955/-959) at 6000 TX-18 surfaced by Cleanview/Distilled; Amazon then confirmed.
Disclosed DC capex | $900M initial (3 buildings x $300M, 189,060 sf each); construction window Aug-Dec 2026.
Power complex | 7.65 GW gas (35 turbines: 21x Siemens SGT-800 + 14 large-frame TBD) + 1.8 GW BESS + 750 MWac solar; TCEQ PSDTX1672 issued Jan 21, 2026.
Abatement | Jun 22, 2026 Pecos Co. Commissioners agenda: GW Ranch Reinvestment Zone designation + Ch. 312 abatement execution with Pacifico GW LLC.
Construction | Land clearing visible in Airbus satellite imagery dated Jul 24, 2026.
Grid | Off-grid at start; Amazon 'actively exploring' grid transition; no ERCOT queue entry disclosed as of Aug 17, 2026.
Still unfiled | ERCOT interconnection; RRC T-4 for Waha lateral; MPGCD water permits; executed abatement text; financing/EPC; purchase price/deed terms.
Read | June memo's 'tenant-contingent option' verdict superseded: IG anchor in as OWNER. Most credible GW-class project in the Permian.

## Filing Inventory
Filing inventory — chronological public record
All filings/records located for GW Ranch, Pacifico GW LLC, and Amazon in Pecos County through 2026-08-18
Date | Filing / record | Agency / venue | Filing party | ID / reference | Substance
2025-08-04 | Air permit application | TCEQ | Pacifico GW LLC (RN112259775) | 396366 / PSDTX1672 | 7.65 GW gas + 1.8 GW BESS + 750 MWac solar; 35 simple-cycle turbines, 5,000 MW nominal
2025-08-20 | Project launch release | Business Wire | Pacifico Energy | 20250820331187 | GW Ranch announced: 5 GW off-grid power for AI; Pecos County, Hwy 18
2026-01-21 | Air permit issued + technical review | TCEQ | Pacifico GW LLC | PSDTX1672 / notice 181033 | Largest US air authorization; <=33 Mt/yr GHG; turbine mix: 21x Siemens SGT-800 + 14x large-frame (OEM undecided)
2026-01-26 | Permit announcement | Business Wire | Pacifico Energy | 20260126236053 | 'Turbines secured'; first power H1 2027; pathway to 5+ GW
2026-03-13 | Senate EPW minority letter | US Senate EPW | Whitehouse / Heinrich / Van Hollen | - | Scrutiny of largest air permit; Franklin response cites '$200B of AI supercomputers'
2026-05-11 | Commissioners Court presentation | Pecos County | Pacifico Energy | Agenda 5/11/26 | GW Ranch development presentation
2026-06-22 | Reinvestment zone + Ch. 312 abatement | Pecos County Commissioners Court | Pacifico GW LLC | Agenda 6/22/26 items 5-7 | Public hearing + resolution designating GW Ranch Reinvestment Zone; execute tax abatement agreement with Pacifico GW LLC; $1,000 admin fee
2026-07-24 | Satellite imagery (Airbus DS) | - (Cleanview analysis) | - | - | Land clearing / early construction visible at site
2026-08-01~07 | Construction registration, Bldg A | TDLR | Amazon (Amazon Data Services) | TABS2026026954 | Pecos County Data Center Bldg A, 6000 TX-18; 189,060 sf; $300M; Aug-Dec 2026
2026-08-01~07 | Construction registration, Bldg B | TDLR | Amazon (Amazon Data Services) | TABS2026026955 | Pecos County Data Center Bldg B; 189,060 sf; $300M; Aug-Dec 2026
2026-08-01~07 | Construction registration, Bldg C | TDLR | Amazon (Amazon Data Services) | TABS2026026959 | Pecos County Data Center Bldg C; 189,060 sf; $300M; Aug-Dec 2026
2026-08-07 | Ownership confirmation + statement | aboutamazon.com / press | Amazon | - | Confirms acquisition of GW Ranch site; grid-transition intent; brackish water; produced-water reuse; 'thousands of jobs'
2026-08-17 | Grid-transition reporting | Data Center Knowledge | Amazon | - | 'Actively exploring' front-of-meter transition; no ERCOT queue entry disclosed

## Negative Findings
Searched, not found — open filing gaps
Public records searched through 2026-08-18 with no responsive filing located
Record | Venue | Status | Why it matters
ERCOT large-load / generation interconnection request | ERCOT | Not disclosed | Amazon states grid-transition intent; a queue entry is the first hard signal and prices SB6 exposure
T-4 pipeline permit, ~15-mi 1 Bcf/d Waha lateral | RRC | Not located | Gas supply chain's first hard filing; operator identity reveals midstream partner
Water well permits (>17.5 gpm non-exempt) | Middle Pecos GCD | Not located | Brackish plan stated but unpermitted; filings name landowner of record (should read Amazon SPV)
Executed Ch. 312 abatement text | Pecos County registries | Agenda-level record only | Recites property interest + buildout schedule verbatim; confirms beneficiary post-sale
Deed / purchase instrument, Amazon acquisition | Pecos County Clerk | Terms not disclosed | Names Amazon land SPV; price; mineral/water reservations
Project financing or EPC mandate | - | None announced | Largely mooted by Amazon ownership but defines Pacifico's residual economics
Large-frame turbine order (14 units) | - | OEM undecided per TCEQ review | Critical path to 5 GW / 2031 given ~3-yr frame-turbine lead times

## Capacity & Specs
Permitted capacity and technical specifications
Per TCEQ PSDTX1672 / application 396366 and technical review (Jan 21, 2026); Amazon/Pacifico disclosures
Component | Value | Unit | Detail / source
Gas-fired generation (permitted) | 7650 | MW | TCEQ PSDTX1672; largest US air authorization on record
Gas-fired generation (nominal, 35 turbines) | 5000 | MW | TCEQ technical review: 35 simple-cycle turbines
- Siemens SGT-800 units | 21 | turbines | TCEQ technical review; ~57 MW class aero-derivative bridging
- Large-frame units (OEM undecided) | 14 | turbines | TCEQ technical review
Battery storage | 1800 | MW | Pacifico project scope
Solar | 750 | MWac | Pacifico project scope
GHG cap | 33000000 | t CO2e/yr | Permit maximum; would be largest single US emissions source if fully utilized
Criteria pollutants | 12000 | t/yr (>) | Regulated pollutants authorized
Site | 8000 | acres | 8,000-8,400 ac; Hwy 18, ~11-17 mi N of Fort Stockton; 31.1621, -102.8964
Data center buildings (filed) | 3 | buildings | TDLR Bldgs A/B/C; 189,060 sf each
Disclosed DC capex (filed) | 900000000 | USD | 3 x $300M per TDLR registrations
Gas demand (full build, est.) | 1.5 | Bcf/d (1-2) | Rice/Baker Institute estimate at permitted capacity
Full-build investment (est.) | 12000000000 | USD | Forbes Feb 2026, quoting Franklin

## Timeline
Project timeline — filed, observed, and targeted milestones
Filed/observed = public record; Target = developer/Amazon statements
Date | Type | Milestone
2025-08-04 | Filed | TCEQ air permit application PSDTX1672 submitted
2025-08-20 | Announced | GW Ranch project publicly launched by Pacifico
2026-01-21 | Filed | TCEQ air permit issued; turbine mix disclosed in technical review
2026-03-13 | Filed | Senate EPW minority letter
2026-05-11 | Filed | Pacifico presentation, Pecos County Commissioners Court
2026-06-22 | Filed | GW Ranch Reinvestment Zone + Ch. 312 abatement with Pacifico GW LLC on Commissioners agenda (execution stage)
2026-07-24 | Observed | Land clearing visible, Airbus satellite imagery
2026-08-01~07 | Filed | Amazon TDLR registrations, Bldgs A/B/C ($900M); construction Aug-Dec 2026
2026-08-07 | Announced | Amazon confirms ownership of GW Ranch site
2026-12-31 | Target | TDLR construction window ends for Bldgs A/B/C
2027-Q1/H1 | Target | First power (Amazon: Q1 2027; Pacifico releases: Q1/H1 2027)
2028 | Target | 1 GW online
2031 | Target | 5+ GW online (slipped from 2030 in earlier releases)

## Entities & Partners
Entities, roles, and partner map
As disclosed through 2026-08-18
Entity | Role | Detail
Amazon / Amazon Data Services | Site owner + data center developer + power offtaker | Acquired 8,000-ac site; filed TDLR Bldgs A/B/C; will purchase power from Pacifico; states grid-transition intent
Pacifico GW LLC (RN112259775) | Project SPV; air permit holder; abatement counterparty | TCEQ PSDTX1672; Ch. 312 agreement per Jun 22 agenda
Pacifico Energy Group LLC | Parent developer (founder Nate Franklin) | San Juan Capistrano, CA; founder-controlled; power developer/seller to Amazon
Siemens Energy | Turbine OEM (partial) | 21x SGT-800 per TCEQ technical review; no public order confirmation from Siemens located
Large-frame turbine OEM | Undecided | 14 units; OEM undecided at permit time; no order announced
Pecos County | Ch. 312 abatement grantor | GW Ranch Reinvestment Zone; Judge Shuster/EDD Ramos on record favorable
Middle Pecos GCD | Groundwater regulator | No well permits located; brackish-zone jurisdiction issues acknowledged by district
Midstream partner (Waha lateral) | Undisclosed | ~15-mi, 1 Bcf/d lateral planned; no RRC T-4 located
EPC contractor | Undisclosed | None announced
Dhiraj Shangari (Pacifico CFO) | Financing lead | Hired Nov 2025, ex-Northland Power; no mandate announced

## TX GW-Class Comps
Texas GW-class off-grid / BTM comparable set
Status as of 2026-08-18; from June memo, updated for GW Ranch
Project | County | Scale | Status (Aug 2026) | Model
GW Ranch (Amazon / Pacifico) | Pecos | 7.65 GW permitted; 5+ GW by 2031 | Amazon owns site; clearing underway; $900M TDLR filings; abatement at execution | Off-grid gas+BESS+solar, grid transition planned
Stargate Abilene (Crusoe/Oracle/OpenAI) | Taylor | 1.2 GW campus; 4.5 GW gas JV | Phase 2 energizing mid-2026 | Grid-tied + BTM gas
Fermi 'Matador' | Potter | 11 GW HyperGrid | Stock -80%+ from IPO; class actions; tenant walkaway | Off-grid 'power island'
Poolside/CoreWeave Horizon | Pecos | 2 GW | Anchor lease terminated Mar 2026; site idle | BTM Permian gas
LandBridge/PowerBridge Alpha | Reeves | 2 GW | First power target 2027 | Co-located gas near Waha
Microsoft (reported) | Reeves | 2.5 GW (reported Apr 2026) | Unconfirmed/reported | TBD
Lancium | Taylor/Childress/Pecos | 1.2 GW+ portfolio | Operating/expanding | Grid-interactive BTM

## Sources
Source register
Primary records first; trade press cited for data only
Source | Date | URL / reference
TCEQ air permit PSDTX1672 / app 396366 + technical review | 2026-01-21 | TCEQ records; construction permit source analysis (Pacifico GW LLC)
TDLR registrations TABS2026026954 / -955 / -959 | 2026-08 | TDLR TABS database
Pecos County Commissioners Court agendas | 2026-05-11 / 06-22 / 07-13 | co.pecos.tx.us
Amazon statement — Pecos County data center | 2026-08 | aboutamazon.com/news/company-news/amazon-pecos-county-texas-data-center-clean-energy-jobs
Distilled/Cleanview scoop (TDLR IDs, Airbus imagery, Amazon confirmation) | 2026-08-07 | distilled.earth / newsletter.cleanview.co
DataCenterDynamics — Amazon acquires 8,000-acre site | 2026-08 | datacenterdynamics.com
ENR — Amazon discloses ownership of GW Ranch | 2026-08 | enr.com/articles/63464
Data Center Knowledge — grid transition | 2026-08-17 | datacenterknowledge.com
US Data Center Projects — TDLR filing details | 2026-08 | usdatacenterprojects.com
Pacifico Energy releases | 2025-08-20 / 2026-01-26 | Business Wire 20250820331187 / 20260126236053
US Senate EPW minority letter | 2026-03-13 | epw.senate.gov
LRP baseline memo | 2026-06-12 | outputs/reports/pacifico-gw-ranch-diligence-2026-06-12.md